## Issues
# | Date Discovered | Module | Type | Severity (QA view) | Description (what the user experiences) | Root Cause | Possible Corrective Action | DIT (existing Development Issue Tracking match)
1 | 2026-09-16 04:00 | Lot Management / Dynamic UI (all Dynamic UI pages) | Defect | Critical | A user holding only LE_View_Lots (Add / Edit / Delete icons disabled, double-click opens the read-only View window, Excel Import hidden) can still add, edit and delete lots by calling the server directly. Confirmed live: posting AddRecord with oper=edit changed a lot (U3 = "srv-edit"), oper=add created a new lot, and a GET to DeleteRecord (after selecting the row) deleted a lot. The delete call answers an HTTP 500 "Runtime Error" page even though the lot is deleted, so the caller cannot tell it worked. Delete is a plain GET with no anti-forgery token. The same framework serves Label Types, Facilities, Print History and other Dynamic UI pages, so they are likely affected too. Requirement LM.150420.F.1.12 (server-side enforcement) is still unmet. | LE_Add_Lots / LE_Chg_Lots / LE_Del_Lots / EI_Lots are checked only at page Load() (icon and menu visibility). DynamicUIController.AddRecord / DeleteRecord / SubmitExcelImport and DynamicUIService.InsertRecord / UpdateRecord / DeleteRecord / Import have no authorization check. DeleteRecord has no [HttpPost] and no anti-forgery token, and throws after deleting (500 after the delete has been committed). | Check the definition's Can* process for the current user in the controller AND the service for every write (add / edit / delete / import / excel import) and return a proper "not authorized" JSON; make DeleteRecord and SubmitExcelImport [HttpPost] with anti-forgery validation; make DeleteRecord return JSON instead of throwing; add regression tests for each process. | None found
2 | 2026-09-16 04:00 | Browser Printing (MDM integration) | Defect | Critical | An MDM item's approved / effective status is checked once when the item is entered in the print wizard. If the item is retired or made ineffective after item entry and before the final Print click, the label still prints with the stale master data (violates FRS MDM20150514100F1.0.2). The operator sees a normal successful print. | The status is cached in PrintSubSession (PrintMasterItem.cs, PrintSubSession.cs, PrintOptionSelectionController.cs) for the rest of the wizard; the final Print submit never re-validates it. | Re-validate the MDM item's approved/effective state (and refuse with a message) at final Print submit, not only at item entry; add a regression test (SC-10). | None found
3 | 2026-10-02 04:00 | Label Control | Defect | Low-Medium | Load Filters restores the saved Column / Operator / Value criteria but resets the LCN Status, Attachments and Label Master dropdowns to their defaults, even though Save stores them. A user reloading a saved filter silently gets a broader result set than the one saved. | FilterSet.load() in Innovatum.Pages.LabelControl.MVC/Scripts/innovatum/FilterSet.js assigns the saved name STRING to Knockout observables that are bound to option OBJECTS (the constructor maps strings to objects; load() does not), so Knockout resets them. | In FilterSet.load() map the saved RecordStatus / AttachmentFilter / LabelMasterFilter names to the matching option objects before assigning (same mapping the constructor uses); add a save/load round-trip test. | None found for this symptom. Related Label Control filter DITs: #5602 (Load Filter "Update version error"), #6064 (error loading public filter).
4 | 2026-10-02 04:00 | Label Control - Mass Update Versions | Observation / to confirm | Low | The job detail "Item Version" column shows the version the record had BEFORE the update (a successful v0 -> v1 update still lists 0; a following no-op job lists 1), which can read as if the update did not happen. The grid also does not show the Version column by default and lists an item's version rows in random order, so versions cannot be told apart without adding the column. | The job detail reads the version stored when the job was submitted, not the result; the grid has no default sort and the Version column is optional. | Show "version before -> after" (or the resulting version) in the job detail; sort version rows by item and version descending by default and include Version in the default columns. | None found
5 | 2026-10-04 04:00 | Security Management | Defect | Critical | A user who can only VIEW Security Management (holds View_Security but not Security_EditSecurity / Security_EditUsersAndGroups) sees greyed-out icons and disabled process checkboxes, but can still change any group's or user's authorizations by sending the same request the page sends (POST /InnoPages/Security/UpdateSecurityProcess). In testing the server answered Success and the group really gained the process (reproduced 3 of 3 runs, then reverted). Any such user could grant themselves or others any process, including Security_EditSecurity (privilege escalation; 21 CFR Part 11 access-control concern). | SecurityController.UpdateSecurityProcess / UpdateAllSecurityProcesses / UpdateUser / UpdateGroup and SecurityService.ToggleSecurityProcess perform no permission check. They only pass HttpContext.User.Identity.Name through for the audit record. The Security_Edit* processes are checked only in GetDataForEdit / GetExistingSecuritySettings to decide what to RENDER, i.e. enforcement is UI-only. | Enforce authorization on the server for every write action: add [Authorize(Roles = "Security_EditSecurity")] (processes) and [Authorize(Roles = "Security_EditUsersAndGroups")] (users/groups) on the controller actions and re-check in SecurityService; add an anti-forgery token; add negative tests that post the endpoints as a view-only user. Review other write endpoints in the same plugin (UpdateUser, UpdateGroup, UpdateAllSecurityProcesses were read, not posted). | None found
6 | 2026-10-04 04:00 | Master Data Management (RobarMasterData seed) | Defect | Low-Medium | Two RobarMasterData fields share the share name md_charname2: "Characteristics Name 2" and "Characteristics Name 3". Consumers that look up md_charname3 (RegAffairs, Wright ItemDocs) cannot find Characteristics Name 3, and label/GUDID mappings bound to md_charname2 get two candidate fields. The Schemas editor itself refuses duplicate share names, so this came in through the install seed. | Copy/paste typo in Innovatum.Install/ROBARDB/MasterDataIntegrity/MasterDataLinkedSchemaFieldsIntegrity.cs (line ~396): Name 3 is generated with "md_charname2" where "md_charname3" is intended (its sibling Value/UOM fields use md_charval3 / md_charuom3). | Change the seed to md_charname3 and add an upgrade script that corrects existing installations (and any template bindings). | None found
7 | 2026-10-04 04:00 | Master Data Management - Save Search | Defect | Medium | Save Search with "Save As New" and a name that already exists silently OVERWRITES the existing saved search (no "name is already taken" message); the dialog just closes and the old search now holds the new criteria - quiet loss of a saved filter. | The Save As New path does not check for an existing name (the script expects "The name is already taken. To save over an existing set, select it from the drop-down."). | Validate the name on Save As New and show the message (or ask for confirmation to overwrite). | None for this symptom. Related Save Search DITs (same area, different defect): #6536 (MDM Overwrite - Description not saved, Published In Val), #6537 (Campaign Manager equivalent).
8 | 2026-10-04 04:00 | Master Data Management - Reset | Observation / to confirm | Low | MDM's Reset button does not clear the filter row (Column / Operator / Value and For Items stay as they were), unlike Label Control's Reset. | Reset restores only some page state; the criteria row is not cleared. | Make Reset clear the criteria row and restore the default columns / page size / limit (as DIT #6535 does for the public-filter case). | Related: #6535 (Master Data public filter and Reset not resetting to defaults, Published In Val)
9 | 2026-10-04 04:00 | Master Data Management - Excel Import | Observation / to confirm | Low-Medium | (1) A failed job's "Download Spreadsheet" returns the uploaded workbook unchanged, without the per-row errors - the only place the errors appear is the on-screen Errors Only grid. (2) The Job Detail "Error Message" line shows the uploaded file name even on a fully successful job; the status reads "ValidationErrors" (no space); a missing-column failure shows an empty Errors Only grid ("No records to view") which looks like "no errors". (3) A mixed sheet (one valid row + one row with a blank required cell) imports NOTHING. (4) Overwriting an approved record by import silently creates an unapproved v1. | The download endpoint streams the stored upload, not a results workbook; job detail binds the file name into the message field; validation is all-or-nothing per file. Not diagnosed further. | Generate a results workbook with an Error column; show the file name in its own field and a clear message for missing columns; confirm intended all-or-nothing behavior and the silent v1 creation with the owners. | None found
10 | 2026-10-04 04:00 | Master Data Management - View History | Observation / to confirm | Low | The history grid shows the same user in two spellings (MBUser1 on field edits, mbuser1 on the approval row) while the Change User filter lists only one. Header changes (Description, Effective dates) are not in Change History; approval logs ApprovalDateTime with a date-only value and does not log Approved By. | The user name is written with different case by different write paths; only schema fields and ApprovalDateTime are audited. | Normalize the user name on write; confirm the audit expectation and add header fields / Approved By to the history if required. | Related (different symptom): #6553 (Master Data Change History "View Detail" links broken)
11 | 2026-10-04 04:00 | Master Data Management (Schemas) | Observation / to confirm | Low | In the Schemas editor: (1) after the "This field is required." error on an empty Schema Name, the first Submit click with a valid name sends no request (second click does); (2) a Dropdown List field with no source makes the whole schema unsaveable with the generic "Invalid fields highlighted or marked with * must be corrected." and only a small * marks the field; (3) while any field is invalid the "Add New Field" link silently does nothing. | Client-side validation state is not cleared/re-evaluated on the first Submit; error summary does not name the invalid field; Add New Field is blocked silently while invalid. | Re-validate and submit in one click; name the invalid field in the error dialog; show a message when Add New Field is blocked. | None found
12 | 2026-10-04 04:00 | Template Management | Observation / to confirm | Low-Medium | Reset does not clear "Filter by Data Source": the checkbox and chosen share names come back after Reset or reload (they persist per user until a Retrieve with the box unticked), so a stale filter silently narrows every later search. "In" / "Not In" accept only comma-separated values (semicolon = no match) without saying so. The Approved dropdown and criteria rows are simply ANDed (the script describes the filter taking precedence). | Reset restores the criteria rows but not the data-source filter state held in the per-user session. | Make Reset clear the data-source filter too, or show it clearly as applied; state the comma-separated format; update the script. | Related: #6439 (Template Management Reset button broken)
13 | 2026-10-04 04:00 | Security Management / Login | Observation / to confirm | Low | A user whose group lacks Login_WebMenu gets "User not authorized for this task." at login with no hint which process is missing; a new group with no processes therefore creates users who cannot log in. Groups and users can never be deleted from the UI (users can only be deactivated), so typo/test groups accumulate. A group Description is required although the script only lists the blank Group error. | The login form checks Login_WebMenu and shows the generic message; no delete function exists for groups/users. | Name the missing process in the message; default new groups to include Login_WebMenu; consider delete for unused groups. | Related enhancement requests (not the same issue): #5553 (allow removing unused security groups), #5552 (allow removing inactive users)
14 | 2026-10-05 04:00 | Workflow Management / View And Vote | Defect | Medium | The rule "Comments are required for rejected workflows" (for users without WM_ViewAndVoteSkipComment) only fires when a row's Detail dialog is opened with Reject ticked and an empty comment. A user without the skip-comment process can tick Reject on the vote grid, sign, and the rejection completes with NO comment (job Status Completed). The requirement reads as if a blank comment is always refused for such users. Also, without WM_ViewAndVoteCheckBox every vote checkbox is silently disabled, with no message saying which process is missing. | RejectRequiresComment (= !User.IsInRole("WM_ViewAndVoteSkipComment")) is evaluated only in the client script (JobSubmission.cshtml showRejectCommentDialog, called from the Detail dialog / beforeClose). The server-side vote submission does not re-check that a comment exists for reject votes. CanCheckBoxes / CanCheckAll simply disable the inputs. | Validate on the server (vote submit) that a reject vote has a comment unless the user holds WM_ViewAndVoteSkipComment, and also run the client check when Reject is ticked on the grid / when Update is clicked. Add a tooltip or message naming the missing process on disabled vote checkboxes. | None found
15 | 2026-10-05 04:00 | Print History Inquiry (Dynamic UI) / InnoView | Defect | Medium | Test Prints never appear in Print History (neither the Dynamic UI page nor the InnoView "View Print History" report). A tester who runs a Test Print and then looks for it in Print History finds nothing. | The forced-filter stored procedure SP_PrintHistoryForcedFilter always filters on [PrintStatus] = 'Printed'; Test Prints are stored with status TestPrinted. (DIT #6600 records the identical root cause.) | Update SP_PrintHistoryForcedFilter to include 'TestPrinted' (as stated in DIT #6600). | #6600 (Ready for Publish) - same issue and same root cause
16 | 2026-10-05 04:00 | Field Definitions Management | Defect | Low-Medium | Criteria filters pass the value to SQL LIKE unescaped: in a Contains filter the underscore is a one-character wildcard (Sharename Contains "C_" also returns F_City and F_Misc1), so literal prefix searches on share names are unreliable. Limit Results and a leftover blank criteria row are also remembered per user and later make Retrieve return truncated or empty results with no message (a blank row once crashed the tab). Field definitions can never be deleted. | The filter value is concatenated into a LIKE pattern without escaping % and _ ; persisted per-user grid state is re-applied on load without being shown; no delete is implemented for field definitions. | Escape LIKE wildcards (or offer a "starts with / exact" operator); show persisted filter state and a "no results because of limit" message; confirm whether delete should exist. | None found
17 | 2026-10-05 04:00 | Workflow Management / View And Vote | Observation / to confirm | High (needs decision) | With WFRejectHasVetoPower = N (the default and the TST703 value) a workflow can end APPROVED even though one voter rejected: two groups [user A group 1, user B group 2] - A rejects (workflow stays Open), B approves -> final status Approved. The same happens for one reject plus one approve inside a single parallel group. With a Veto step (Vote Counts As Veto) a reject closes the workflow Rejected at once. Also, a later approval group can be voted BEFORE the earlier group (group 2 voted while group 1 was still pending); the order only affects notification e-mails. This is a requirements gap, as there are no requirements in Valmaster that cover this. | WFViewAndVoteService.cs (~line 1331): "If the global setting WFRejectHasVetoPower is off the workflow header status will be determined by the last vote." ValMaster only says rejects can optionally have veto power and that the header status is updated "by reviewing all the workflow steps"; the mixed-vote outcome with veto off is not defined (WMPreApproveUser requirement says a rejected prior step rejects the whole workflow). | Decide the intended rule (last vote wins vs any reject rejects) and document it in the requirement and formal scripts; if "any reject rejects", change the header-status calculation to consider all steps; decide whether later approval groups may vote early and either enforce the order or document that it is notification-only. | None found
18 | 2026-10-05 04:00 | Workflow Management - Preset Management | Observation / to confirm | Low-Medium | "Update Step" and "Delete Step" act immediately with no confirmation (only deleting a whole preset asks), so one click loses a step; Active / Description changes are saved only by "Submit Changes" and are silently discarded when another preset is selected (no unsaved-changes warning). | The step form posts directly; the preset header form has no dirty-state check when switching presets. | Add a confirmation for Delete Step (and optionally Update Step) and an "unsaved changes" prompt when switching presets. | None found
19 | 2026-10-05 04:00 | Workflow Management - search grid | Observation / to confirm | Low-Medium | Choosing a Column in the Advanced Options criteria row crashed the browser tab repeatedly in automated runs (headless and headed). The last search (user / status / criteria) is persisted and re-applied on page load, and the grid defaults to ascending Workflow ID so new workflows land on the last of 80+ pages. For a workflow with several steps where some are voted, the "Last User" column is blank in the grid. | Not diagnosed for the crash; persisted search state is re-applied by design; default sort is ascending. The blank Last User is DIT #6233. | Investigate the criteria widget crash; default the grid to newest-first; fix the Last User population (#6233). | #6233 (Workflow Management - Last User not populated for multi-step workflows) for the Last User part; none for the others
20 | 2026-10-05 04:00 | Workflow Management - item / template workflows | Observation / to confirm | Low | Approving an item or template workflow sets Approved By to the WORKFLOW ID (e.g. "20261005-0017 - 10/5/2026"), not the voting user. While the workflow is open the item shows "Item being routed in workflow - cannot be modified." and the Approve Item tooltip says "User not authorized for this task 'CM_MassApprove'", which reads like a permission problem rather than a lock. The vote result page shows "Percent Complete 100 %" on some pages and "100%" on others. | By design for traceability (the voter is in the workflow history); the tooltip reuses the authorization message for the locked state; two pages format the percentage differently. | Confirm the audit intent; use a "being routed in workflow" tooltip for the lock; format the percentage consistently. | None found
21 | 2026-10-06 04:00 | Multi Document Printing / InnoPages host | Observation / to confirm | Low | A user without BP_MultiDocumentPrint who opens the page URL directly is redirected to /InnoPages/Host/LoginRedirect?ReturnUrl=... which shows the raw ASP.NET page "Server Error in '/InnoPages' Application. The resource cannot be found." (HTTP 404) instead of a "not authorized" message. The tile is simply missing from the menu. Probably the same for any InnoPage whose [Authorize(Roles=...)] fails. | The InnoPages host redirects unauthorized requests to Host/LoginRedirect, which has no route/view in the deployed host (404) so IIS shows the default error page. | Provide a LoginRedirect / Unauthorized page (or route) in the InnoPages host that explains "User not authorized for this task <process>" and links back to the Web Menu. | None found
22 | 2026-10-06 04:00 | Workflow Management / Edit Workflows | Defect | Medium | Deleting the LAST OPEN step of a workflow (Edit Workflows > Delete User, all other steps already voted) leaves the workflow with status Open forever: nothing is votable any more and it stays in Open Only lists (about 10 orphaned test workflows were found). It can only be recovered by adding a new step (Add User at End). Also: editing a mix of voted and unvoted workflows reports "Completed" for the voted one with the message "User X has already voted or does not exist." and changes nothing for it; a step user added with Edit Workflows shows with a blank Department. | The step-delete job does not re-evaluate the workflow header status after removing the last open step (the status is only recalculated when a vote is cast). | After deleting/replacing steps, recalculate the workflow header status (close it as Approved/Rejected when no open step remains) or warn that no voter will remain; make the job message distinguish "no change - already voted" from success; carry Department when adding a step. | None found
23 | 2026-10-06 04:00 | Lot Management | Defect | Medium | No Lots field is required on TST703: a completely blank record (blank order, lot and item number) is accepted (a second identical blank record is refused with "Record already exists", as is a duplicate order/lot/item/entity), and a lot for a NONEXISTENT item number is accepted too. The "Row N is missing a value for the X column which is specified as Required" import validation is therefore unreachable on this environment. | The fresh-install seed (DynamicUIDetailDefaultRecords.cs) marks Lots.ItemNumber Required = Y, but the upgrade script (Robar/DB/UpgradeScripts/DynamicUI_LotManagement_Upgrade.sql) ships every Lots field Required = N, violating the "seed data must mirror the upgrade script" rule; no item-existence validation is applied on insert. | Make the upgrade script and the seed agree (Order/Lot/Item required) and add item-existence validation; provide an upgrade script that sets Required for existing installations. | None found
24 | 2026-10-06 04:00 | Lot Management - Save Search / Load Search | Observation / to confirm | Low | Saving a search under an existing name overwrites the criteria but keeps the OLD description; Load Search restores the criteria only (not the sort or page); there is no way to delete a saved search from the UI. | The save routine updates the criteria column only; no delete action exists in the dialog. | Update the description on overwrite (or prompt), and add a delete option for saved searches. | None found
25 | 2026-10-07 04:00 | Print by Lot - Printers dropdown | Observation / to confirm | Low-Medium | When Printer Control has no "*" (default) record the Printers dropdown on Print by Lot is empty with no message, so the user cannot print and gets no explanation. The legacy Print button also needs a genuine user click: without user activation the browser silently blocks the sentinel: launch and the page reports "Timeout waiting for Sentinel." / status Failed after 100 s. | Printer list is built from Printer Control records; the sentinel: protocol launch is blocked by Chrome without a user gesture (automation artifact). | Show a "No printers configured" message; (the click issue is an automation artifact, not a defect). | Related: #6511 (Print History Exact Reprint - "Timeout waiting for Sentinel.") - same message, different path
26 | 2026-10-07 04:00 | Password settings - other inconsistencies | Defect | Low-Medium | ChangeOnReset has no effect (dead setting); Password Change needs no login and accepts new password = current; error messages are generic; a disabled user is shown as "Locked"; the button is labelled Reset in one place and Cancel in another; the seed user never expires. | Settings are read from LegacySettings and cached per process; several screens implement their own checks. | Centralize validation, remove or wire the ChangeOnReset setting, and make messages and labels consistent; document the restart requirement after changing password settings. | Related: #6512; none for the rest
27 | 2026-10-08 04:00 | Codes Management - Excel Import | Defect | Medium | In Codes Excel Import an Active value of "Maybe" passes validation ("Validation Successful"), but Begin Upload then fails with an EMPTY red error dialog (no message) and nothing is created. The same empty dialog appears for a file with only NEW rows when the signer lacks EI_Codes. | The validator is meant to accept only Y/N/YES/NO/1/0, but Convert.ToChar("Maybe") in CodesDataValidator.ConvertRowToEntity (likely) throws later. The EI_Codes right is checked server side in ImportData, not at the signature step, and that message is blank. | Validate Active against the allowed values; show a real message for a missing EI_Codes right (requirement CM.160202.F.4.1: "User not authorized for this task EI_Codes"). | Related: #5993 (Codes Management Excel Import, different symptom: Previous Page link); none for this symptom
28 | 2026-10-08 04:00 | Codes Management - signer rights / messages | Observation / to confirm | Low-Medium | The signer check names only EI_Codes_Upd when both EI_Codes and EI_Codes_Upd are missing, and checks the rights only when the file contains rows that already exist. The message "Code Type exceeds the maximum allowed 30 chararacters length" has a typo. | In the controller Authenticate method the second assignment overwrites the first; the typo is in Localize_Codes.cs. | Name both missing processes (or check them independently); fix the typo. | None found
29 | 2026-10-08 04:00 | Codes Management - filters | Observation / to confirm | Low | A Contains filter with an empty value does not reload the grid (the previous result stays); Greater Than / Less Than compare as text ("0185" vs "0187"); filters are not remembered when the module is reopened; the grid loads all ~190 codes with no limit. | Not diagnosed (generic filter behavior of the page). | Confirm whether these are intended; consider numeric comparison and a row limit. | None found
30 | 2026-10-08 04:00 | Print by Lot / print screens - AddLotReasonRequired | Observation / to confirm | Low-Medium | With AddLotReasonRequired = Y the lot record is created as soon as the Lot Panel appears (placeholder dates 01/01/1900), before anything is printed. A user who answers the Reason Code dialog and then abandons the screen leaves an empty lot behind (and the reason is already recorded). | The lot is inserted when the Lot Panel is shown, not when the first label is printed. | Confirm whether the lot should only be created at print time. | None found
31 | 2026-10-08 04:00 | Lot Management / inactive Print Entity | Observation / to confirm | Low-Medium | For a user who has an INACTIVE entity assigned the Lot Management Add icon is disabled even when an active entity is also assigned, whereas the print screens correctly ignore the inactive entity. | Not diagnosed (the modules treat inactive entities differently). | Make Lot Management ignore inactive entities like the print screens. | None found
32 | 2026-10-08 04:00 | Destination Labeling - Create Order | Defect | Medium | Re-entering an existing order number and clicking Create Order shows the unlocalized exception text "Localizable Exception thrown with ResourceType: Innovatum.InnoUserException.Err_DestLabeling and ResourceKey: Order_Already_Exists" instead of "Order already exists" (requirements DL.171227.F.5.5 / F.1.4). | The seed exists in source (Localize_DestLabeling.cs and DestLabeling_Upgrade.sql) but the LocalizationResourceDef row is missing in the TST703 database (environment / upgrade gap, checked 2026-10-10). | Run the DestLabeling upgrade script / reseed localizations on TST703 and confirm other environments have the row. | None found
33 | 2026-10-08 04:00 | Destination Labeling - barcode scan | Defect | Low-Medium | (1) The "Unable to recognize GS1 data identifier" message lists GTIN(01), Expiration(17), Lot(10), SerialNumber(21) but not Manufactured(11), which the requirement lists. (2) The extra "Barcode Scan" field (#secondBarcodeEntry) of the Barcode Scan dialog is hidden. (3) After all values are entered the dialog stays open under "No print rows found for given barcode" (requirement: it closes). The parenthesized GS1 form "(01)...(10)..." is not accepted. (DL.171227.F.10.9 / F.10.7 / F.10.11) | Not diagnosed. | Align the dialog and message with the requirements. | Related: #6215 (Destination Labeling barcode parse, different symptom); none for these three
34 | 2026-10-09 04:00 | Print by Order / Print Request (batch-quantity reprint) | Defect | Medium | With ReprintBasedOnBatchQty = Y the Reprint box is only forced on AFTER the allowed total has been printed. Allowed 5, 3 already printed: a default Copy of 5 (3+5=8) or a Copy of 3 (3+3=6) does not tick Reprint, so more than the batch quantity can be printed as originals. Requirement FRS-8.1.9.2: forced on when printed + about-to-print exceeds batch x multiplier + extra. | Lot.IsReprint compares only the printed total (>=) with the allowed total; its code comment says the screen-side comparison of printed + copies is "currently not supported". | Implement the comparison of printed quantity + copies to print against the allowed total on the print screens. | Related: #6224 (MDP ignores ReprintBasedOnBatchQty = Y, any second print is a reprint; deferred from 7.0.3); none for the Print by Order threshold
35 | 2026-10-09 04:00 | Multi Document Printing / Label Control Number Printing (requirements conflict) | Observation / to confirm | Medium | LCP.170105.F.10.1 says a template with S_Ser or S_USerial sets Copy to 1 and ignores batch qty / multiplier / extra in ALL printing modules; MDP.180418.F.9.11 says serial copies in Multi Document Printing include Batch Quantity, Multiplier and Extra. Live (S_USerial and S_Ser items, batch 10, Qty2 3, u5 2): Print by Order Copy = 1, Multi Document Printing Copies = 32. | The two requirements contradict each other; the product follows F.10.1 in Print by Order and F.9.11 in Multi Document Printing. | Requirement owner to decide which rule applies to Multi Document Printing. | None found
36 | 2026-10-09 04:00 | Dictionary Management - NewVersion authorization | Defect | High | A user without DM_NewVersion can still create a new dictionary version by posting directly to InnoPages/DictionaryManagement/NewVersion (answers Success true). NewRecord and Update refuse the same user correctly. Confirmed live on TST703 (the probe created an unapproved version of the seeded phrase Batch Number / prompt, id 5819208f-67b5-4f7a-bce6-76bf0c29b020). | DictionaryManagementService.SaveNewVersion checks HasPermissionFor(DM_NewVersion) and fills response.Errors but never sets Success = false or returns, so the method carries on and inserts the version. | Return the not-authorized response right after the check (as SaveDictionary does). | None found
37 | 2026-10-09 04:00 | Security Management - Copy Security Settings From | Defect | Medium | A user with Security_EditUsersAndGroups but without Security_EditSecurity still has the Copy Security Settings From drop-down enabled in the Add User dialog, so such a user can create a user as a copy of any group (privilege escalation). Requirement SE.150915.F.9.2 says the copy is not available without Security_EditSecurity. | Not diagnosed (the dialog does not take Security_EditSecurity into account; the write endpoints also have no server-side check, see the Security Management rows above). | Disable / hide the drop-down without Security_EditSecurity and check it server side. | None found (related enhancements #5623, #5552, #5553 are different)
38 | 2026-10-10 04:00 | Localization (static sweep) | Observation / to confirm | Low | 21 InnoUserException keys used in code have no seed in Default_Localizations or the upgrade SQL (list in the QA notes); only Ajax_User_Not_Logged_In and the Lib.DotNet Password_Invalid key could be user-visible. A raw Localizable Exception text seen on TST703 for Destination Labeling Order_Already_Exists is a missing database row, not a code gap. | Two copies of Exceptions.cs name the invalid-password key differently; some keys were never seeded. | Seed or remove the unused keys; run the DestLabeling upgrade script on TST703. | Related: #3295 (LocalizationResourceDef values need updating)
39 | 2026-10-11 04:00 | Link Management / Attachment Management - filters and wording | Observation / to confirm | Low | Link Management restores the previous session's filter rows (including blank ones) and has no Reset button; Retrieve Data then raises "Filter will take precedence over the search criteria". The Associate Attachments drop-down offers five types (By LCN / Item / Item Version / Template / Template Version) and the switch links on the Link pages read "By Item" etc.; requirements F.6.1 / F.7.9 / F.9.12 / F.11.10 list three types and "Link by ..." wording. | Saved criteria are restored on load; the version types and link captions were added after the requirements were written. | Add a Reset button or clear stale rows; update the requirements for the extra types and captions. | Related: #3427 (precedence message between the Active filter and search criteria); none for the missing Reset
40 | 2026-10-11 04:00 | Label Control - schema security | Observation / to confirm | Low | With Master Data integration on, a user with LC_View_LabelControl but without SCH_<item schema> (for example SCH_RobarMasterData) opens Label Control and sees only "All schemas have been disallowed due to Schema Security"; label type security (LT_<type>) additionally decides which rows are shown. Neither dependency is described in the Label Control requirements. | LabelControlController returns the SchemaSecurity view when the user has no item schema. | Document the dependency in the requirements / help; consider a clearer message. | None found
41 | 2026-10-12 04:00 | Flex Printing - duplicate identifier crashes Next | Defect | Medium | On the Flex Printing screen clicking Next showed the ASP.NET "Server Error" page for ANY input (existing lot, unknown item, blank). The FlexPrinting PrintConfig on TST703 had Flex_Identifier_1 and _3 both FlexLot_ItemNumber (the screen showed Item Number / Lot Number / Item Number). Changing _3 to FlexLot_OrderNum AddOnly made Next work at once. A bad configuration should give a friendly message, not a Server Error. | A duplicate identifier is not rejected by the configuration check in WebPrintFlex (lines 34-58); the failing line was not pinpointed. | Validate duplicate identifiers (show "Insufficient lot identifiers configured" or a config error). | None found
42 | 2026-10-13 | MDM - Retire/untire message missing | Defect | Medium | On Master Data Management, when retiring or unretiring, 'The effective end date will be applied to all items' message is expected in test scripts, but does not display. No requirements in Valmaster around this. | Behavior or seed data differs from what the scripts describe (scripts are stale or the code changed). | Update the formal scripts or align the behavior | None found
Note on B2: First seen in the 2026-09-16 code review; confirmed live 2026-10-06.
Note on B16: Approximate: found in the same Print History session as the HTTP 500; not logged separately.

## Read me
Issues found during the exploratory / Playwright training sessions on TST703 (Suite 7, 7.0.3.20198), 2026-08-25 to 2026-10-12.
Date Discovered = the day the issue was first observed or logged (rows are sorted by it, oldest first). It comes from the date on the matching row of .agents/dit-tracker.md or, for the August findings, from the exploratory session log of that day. Where the date is approximate or the issue was first seen earlier than it was confirmed, the cell has a note (hover the red corner). The rows added on 2026-10-09 / 10 were matched against the DIT sheet on 2026-10-11 (the 53 tickets of the affected modules were read; keyword matching only, so a manual look is still worthwhile).
Columns: Description = the issue and what the user experiences; Root Cause = what in the code/config causes it (or "Not diagnosed" when it could not be traced); Possible Corrective Action = what would fix it; DIT = an existing Development Issue Tracking ticket that matches.
Type: Defect = reproduced / confirmed; Observation = behavior to confirm with developers (may be by design)
DIT colors: green = the DIT describes the same issue; blue = related ticket only (same area / different defect); no color = no matching DIT found.
How DIT matches were found: the Development Issue Tracking sheet (459 rows) was searched READ-ONLY by module and symptom keywords (Description, Root Cause and Corrective Action columns). Nothing in the DIT sheet was changed. A "None found" means no ticket with a matching description was found by those searches - a manual look by someone who knows the history is still worthwhile.
Root causes marked as read from code come from the 7.0.3 source tree on the QA workstation. Items marked "Not diagnosed" need server/IIS logs or database access to trace.
Several rows were confirmed live with Playwright specs under ROBAR_Tests (see .agents/dit-tracker.md for the spec names and the full history). Nothing has been filed or sent to developers from these sessions.